## Planning Table
Line No. | Priority Group | Main Issue / Feature | Section | Line Type | Original Text | Status | Completion % | Notes
1 | Must Have (MVP) |  | Priority heading | Priority heading | Must Have (MVP) | Done | 100%
2 | Must Have (MVP) | Home Page / Card Creation Page | Feature heading | Feature heading | Home Page / Card Creation Page | Done | 100%
3 | Must Have (MVP) | Home Page / Card Creation Page | User request | Section heading | User request: | Done | 100%
4 | Must Have (MVP) | Home Page / Card Creation Page | User request | Detail line | As a visitor, I want to understand what ThankUCard does and start creating a thank-you card easily. | Done | 100%
5 | Must Have (MVP) | Home Page / Card Creation Page | User request | Blank line |  | Not Started | 0%
6 | Must Have (MVP) | Home Page / Card Creation Page | How it can be done | Section heading | How it can be done: | Done | 100%
7 | Must Have (MVP) | Home Page / Card Creation Page | How it can be done | Detail line | Users land on the homepage and see a clear step-based card creation layout. | Done | 100%
8 | Must Have (MVP) | Home Page / Card Creation Page | How it can be done | Blank line |  | Not Started | 0%
9 | Must Have (MVP) | Home Page / Card Creation Page | What needs to be included | Section heading | What needs to be included: | Done | 100%
10 | Must Have (MVP) | Home Page / Card Creation Page | What needs to be included | Blank line |  | Not Started | 0%
11 | Must Have (MVP) | Home Page / Card Creation Page | What needs to be included | Detail line | Homepage template | Done | 100%
12 | Must Have (MVP) | Home Page / Card Creation Page | What needs to be included | Detail line | Navigation menu | Done | 100%
13 | Must Have (MVP) | Home Page / Card Creation Page | What needs to be included | Detail line | Clear project branding | Done | 100%
14 | Must Have (MVP) | Home Page / Card Creation Page | What needs to be included | Detail line | Step 1, Step 2, Step 3 layout | Done | 100%
15 | Must Have (MVP) | Home Page / Card Creation Page | What needs to be included | Detail line | Card creation form area | Done | 100%
16 | Must Have (MVP) | Home Page / Card Creation Page | What needs to be included | Detail line | Preview area | Done | 100%
17 | Must Have (MVP) | Home Page / Card Creation Page | What needs to be included | Detail line | Login/Register links | Done | 100%
18 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
19 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Blank line |  | Not Started | 0%
20 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Detail line | Create Django project | Done | 100%
21 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Detail line | Create base template | Done | 100%
22 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Detail line | Add navbar | Done | 100%
23 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Detail line | Create homepage URL | Done | 100%
24 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Detail line | Create homepage view | Done | 100%
25 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Detail line | Create homepage template | Done | 100%
26 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Detail line | Add basic styling | Done | 100%
27 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Detail line | Add page title and introduction | Done | 100%
28 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Detail line | Add card creation form layout | Done | 100%
29 | Must Have (MVP) | Home Page / Card Creation Page | Tasks to complete | Detail line | Add preview placeholder | Done | 100%
30 | Must Have (MVP) | Home Page / Card Creation Page | Testing checklist | Section heading | Testing checklist: | Done | 100%
31 | Must Have (MVP) | Home Page / Card Creation Page | Testing checklist | Blank line |  | Not Started | 0%
32 | Must Have (MVP) | Home Page / Card Creation Page | Testing checklist | Detail line | Homepage loads correctly | Done | 100%
33 | Must Have (MVP) | Home Page / Card Creation Page | Testing checklist | Detail line | Navbar links work | Done | 100%
34 | Must Have (MVP) | Home Page / Card Creation Page | Testing checklist | Detail line | Page is readable on desktop | Done | 100%
35 | Must Have (MVP) | Home Page / Card Creation Page | Testing checklist | Detail line | Form layout appears correctly | Done | 100%
36 | Must Have (MVP) | Home Page / Card Creation Page | Testing checklist | Detail line | Preview placeholder is visible | Done | 100%
37 | Must Have (MVP) | User Registration | Feature heading | Feature heading | User Registration | Done | 100%
38 | Must Have (MVP) | User Registration | User request | Section heading | User request: | Done | 100%
39 | Must Have (MVP) | User Registration | User request | Detail line | As a new user, I want to register an account so that I can save and manage my cards. | Done | 100%
40 | Must Have (MVP) | User Registration | User request | Blank line |  | Not Started | 0%
41 | Must Have (MVP) | User Registration | How it can be done | Section heading | How it can be done: | Done | 100%
42 | Must Have (MVP) | User Registration | How it can be done | Detail line | User completes a registration form and submits it to create an account. | Done | 100%
43 | Must Have (MVP) | User Registration | How it can be done | Blank line |  | Not Started | 0%
44 | Must Have (MVP) | User Registration | What needs to be included | Section heading | What needs to be included: | Done | 100%
45 | Must Have (MVP) | User Registration | What needs to be included | Blank line |  | Not Started | 0%
46 | Must Have (MVP) | User Registration | What needs to be included | Detail line | Registration form | Done | 100%
47 | Must Have (MVP) | User Registration | What needs to be included | Detail line | Username/email/password fields | Done | 100%
48 | Must Have (MVP) | User Registration | What needs to be included | Detail line | Validation and error handling | Done | 100%
49 | Must Have (MVP) | User Registration | What needs to be included | Detail line | User account creation | Done | 100%
50 | Must Have (MVP) | User Registration | What needs to be included | Detail line | Redirect after successful registration | Done | 100%
51 | Must Have (MVP) | User Registration | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
52 | Must Have (MVP) | User Registration | Tasks to complete | Blank line |  | Not Started | 0%
53 | Must Have (MVP) | User Registration | Tasks to complete | Detail line | Create accounts app | Done | 100%
54 | Must Have (MVP) | User Registration | Tasks to complete | Detail line | Create register URL | Done | 100%
55 | Must Have (MVP) | User Registration | Tasks to complete | Detail line | Create register view | Done | 100%
56 | Must Have (MVP) | User Registration | Tasks to complete | Detail line | Create register form | Done | 100%
57 | Must Have (MVP) | User Registration | Tasks to complete | Detail line | Create register template | Done | 100%
58 | Must Have (MVP) | User Registration | Tasks to complete | Detail line | Add form validation | Done | 100%
59 | Must Have (MVP) | User Registration | Tasks to complete | Detail line | Display error messages | Done | 100%
60 | Must Have (MVP) | User Registration | Tasks to complete | Detail line | Redirect user after registration | Done | 100%
61 | Must Have (MVP) | User Registration | Tasks to complete | Detail line | Add register link to navbar | Done | 100%
62 | Must Have (MVP) | User Registration | Testing checklist | Section heading | Testing checklist: | Done | 100%
63 | Must Have (MVP) | User Registration | Testing checklist | Blank line |  | Not Started | 0%
64 | Must Have (MVP) | User Registration | Testing checklist | Detail line | User can open register page | Done | 100%
65 | Must Have (MVP) | User Registration | Testing checklist | Detail line | User can create account with valid data | Done | 100%
66 | Must Have (MVP) | User Registration | Testing checklist | Detail line | Invalid form shows errors | Done | 100%
67 | Must Have (MVP) | User Registration | Testing checklist | Detail line | Duplicate username/email is handled | Done | 100%
68 | Must Have (MVP) | User Registration | Testing checklist | Detail line | User is redirected after registration | Done | 100%
69 | Must Have (MVP) | User Registration | Testing checklist | Detail line | New user exists in database | Done | 100%
70 | Must Have (MVP) | User Login & Logout | Feature heading | Feature heading | User Login & Logout | Done | 100%
71 | Must Have (MVP) | User Login & Logout | User request | Section heading | User request: | Done | 100%
72 | Must Have (MVP) | User Login & Logout | User request | Detail line | As a returning user, I want to log in and log out securely. | Done | 100%
73 | Must Have (MVP) | User Login & Logout | User request | Blank line |  | Not Started | 0%
74 | Must Have (MVP) | User Login & Logout | How it can be done | Section heading | How it can be done: | Done | 100%
75 | Must Have (MVP) | User Login & Logout | How it can be done | Detail line | User logs in with their credentials and can end their session by logging out. | Done | 100%
76 | Must Have (MVP) | User Login & Logout | How it can be done | Blank line |  | Not Started | 0%
77 | Must Have (MVP) | User Login & Logout | What needs to be included | Section heading | What needs to be included: | Done | 100%
78 | Must Have (MVP) | User Login & Logout | What needs to be included | Blank line |  | Not Started | 0%
79 | Must Have (MVP) | User Login & Logout | What needs to be included | Detail line | Login form | Done | 100%
80 | Must Have (MVP) | User Login & Logout | What needs to be included | Detail line | Authentication handling | Done | 100%
81 | Must Have (MVP) | User Login & Logout | What needs to be included | Detail line | Logout functionality | Done | 100%
82 | Must Have (MVP) | User Login & Logout | What needs to be included | Detail line | Session management | Done | 100%
83 | Must Have (MVP) | User Login & Logout | What needs to be included | Detail line | Navigation changes for logged-in users | Done | 100%
84 | Must Have (MVP) | User Login & Logout | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
85 | Must Have (MVP) | User Login & Logout | Tasks to complete | Blank line |  | Not Started | 0%
86 | Must Have (MVP) | User Login & Logout | Tasks to complete | Detail line | Create login URL | Done | 100%
87 | Must Have (MVP) | User Login & Logout | Tasks to complete | Detail line | Create login template | Done | 100%
88 | Must Have (MVP) | User Login & Logout | Tasks to complete | Detail line | Use Django login view | Done | 100%
89 | Must Have (MVP) | User Login & Logout | Tasks to complete | Detail line | Create logout URL | Done | 100%
90 | Must Have (MVP) | User Login & Logout | Tasks to complete | Detail line | Add logout button/link | Done | 100%
91 | Must Have (MVP) | User Login & Logout | Tasks to complete | Detail line | Show username when logged in | Done | 100%
92 | Must Have (MVP) | User Login & Logout | Tasks to complete | Detail line | Hide login/register links when logged in | Done | 100%
93 | Must Have (MVP) | User Login & Logout | Tasks to complete | Detail line | Redirect after login/logout | Done | 100%
94 | Must Have (MVP) | User Login & Logout | Testing checklist | Section heading | Testing checklist: | Done | 100%
95 | Must Have (MVP) | User Login & Logout | Testing checklist | Blank line |  | Not Started | 0%
96 | Must Have (MVP) | User Login & Logout | Testing checklist | Detail line | User can log in with valid credentials | Done | 100%
97 | Must Have (MVP) | User Login & Logout | Testing checklist | Detail line | Invalid login shows error | Done | 100%
98 | Must Have (MVP) | User Login & Logout | Testing checklist | Detail line | Logged-in user sees account/logout links | Done | 100%
99 | Must Have (MVP) | User Login & Logout | Testing checklist | Detail line | User can log out | Done | 100%
100 | Must Have (MVP) | User Login & Logout | Testing checklist | Detail line | Logged-out user cannot access protected pages | Done | 100%
101 | Must Have (MVP) | Password Reset | Feature heading | Feature heading | Password Reset | Done | 100%
102 | Must Have (MVP) | Password Reset | User request | Section heading | User request: | Done | 100%
103 | Must Have (MVP) | Password Reset | User request | Detail line | As a user, I want to reset my password so that I can regain access to my account. | Done | 100%
104 | Must Have (MVP) | Password Reset | User request | Blank line |  | Not Started | 0%
105 | Must Have (MVP) | Password Reset | How it can be done | Section heading | How it can be done: | Done | 100%
106 | Must Have (MVP) | Password Reset | How it can be done | Detail line | User requests a password reset and follows Django’s password reset flow. | Done | 100%
107 | Must Have (MVP) | Password Reset | How it can be done | Blank line |  | Not Started | 0%
108 | Must Have (MVP) | Password Reset | What needs to be included | Section heading | What needs to be included: | Done | 100%
109 | Must Have (MVP) | Password Reset | What needs to be included | Blank line |  | Not Started | 0%
110 | Must Have (MVP) | Password Reset | What needs to be included | Detail line | Password reset form | Done | 100%
111 | Must Have (MVP) | Password Reset | What needs to be included | Detail line | Password reset confirmation pages | Done | 100%
112 | Must Have (MVP) | Password Reset | What needs to be included | Detail line | Email/backend setup for development | Done | 100%
113 | Must Have (MVP) | Password Reset | What needs to be included | Detail line | New password form | Done | 100%
114 | Must Have (MVP) | Password Reset | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
115 | Must Have (MVP) | Password Reset | Tasks to complete | Blank line |  | Not Started | 0%
116 | Must Have (MVP) | Password Reset | Tasks to complete | Detail line | Add Django password reset URLs | Done | 100%
117 | Must Have (MVP) | Password Reset | Tasks to complete | Detail line | Create password reset templates | Done | 100%
118 | Must Have (MVP) | Password Reset | Tasks to complete | Detail line | Configure email backend for development | Done | 100%
119 | Must Have (MVP) | Password Reset | Tasks to complete | Detail line | Add “Forgot password?” link on login page | Done | 100%
120 | Must Have (MVP) | Password Reset | Tasks to complete | Detail line | Test reset flow locally | Done | 100%
121 | Must Have (MVP) | Password Reset | Testing checklist | Section heading | Testing checklist: | Done | 100%
122 | Must Have (MVP) | Password Reset | Testing checklist | Blank line |  | Not Started | 0%
123 | Must Have (MVP) | Password Reset | Testing checklist | Detail line | Password reset page opens | Done | 100%
124 | Must Have (MVP) | Password Reset | Testing checklist | Detail line | User can submit email | Done | 100%
125 | Must Have (MVP) | Password Reset | Testing checklist | Detail line | Reset email/link is generated in development | Done | 100%
126 | Must Have (MVP) | Password Reset | Testing checklist | Detail line | User can set new password | Done | 100%
127 | Must Have (MVP) | Password Reset | Testing checklist | Detail line | User can log in with new password | Done | 100%
128 | Must Have (MVP) | Select Card Options | Feature heading | Feature heading | Select Card Options | Done | 100%
129 | Must Have (MVP) | Select Card Options | User request | Section heading | User request: | Done | 100%
130 | Must Have (MVP) | Select Card Options | User request | Detail line | As a user, I want to select recipient type, theme, colour, and decorative element so that my card matches my needs. | Done | 100%
131 | Must Have (MVP) | Select Card Options | User request | Blank line |  | Not Started | 0%
132 | Must Have (MVP) | Select Card Options | How it can be done | Section heading | How it can be done: | Done | 100%
133 | Must Have (MVP) | Select Card Options | How it can be done | Detail line | User selects options from dropdown fields managed through the database/admin panel. | Done | 100%
134 | Must Have (MVP) | Select Card Options | How it can be done | Blank line |  | Not Started | 0%
135 | Must Have (MVP) | Select Card Options | What needs to be included | Section heading | What needs to be included: | Done | 100%
136 | Must Have (MVP) | Select Card Options | What needs to be included | Blank line |  | Not Started | 0%
137 | Must Have (MVP) | Select Card Options | What needs to be included | Detail line | Recipient type dropdown | Done | 100%
138 | Must Have (MVP) | Select Card Options | What needs to be included | Detail line | Theme dropdown | Done | 100%
139 | Must Have (MVP) | Select Card Options | What needs to be included | Detail line | Colour dropdown | Done | 100%
140 | Must Have (MVP) | Select Card Options | What needs to be included | Detail line | Element dropdown | Done | 100%
141 | Must Have (MVP) | Select Card Options | What needs to be included | Detail line | Database models for each option | Done | 100%
142 | Must Have (MVP) | Select Card Options | What needs to be included | Detail line | Admin management for options | Done | 100%
143 | Must Have (MVP) | Select Card Options | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
144 | Must Have (MVP) | Select Card Options | Tasks to complete | Blank line |  | Not Started | 0%
145 | Must Have (MVP) | Select Card Options | Tasks to complete | Detail line | Create cards app | Done | 100%
146 | Must Have (MVP) | Select Card Options | Tasks to complete | Detail line | Create RecipientType model | Done | 100%
147 | Must Have (MVP) | Select Card Options | Tasks to complete | Detail line | Create Theme model | Done | 100%
148 | Must Have (MVP) | Select Card Options | Tasks to complete | Detail line | Create Colour model | Done | 100%
149 | Must Have (MVP) | Select Card Options | Tasks to complete | Detail line | Create Element model | Done | 100%
150 | Must Have (MVP) | Select Card Options | Tasks to complete | Detail line | Register models in admin | Done | 100%
151 | Must Have (MVP) | Select Card Options | Tasks to complete | Detail line | Add sample data in admin | Done | 100%
152 | Must Have (MVP) | Select Card Options | Tasks to complete | Detail line | Create card form | Done | 100%
153 | Must Have (MVP) | Select Card Options | Tasks to complete | Detail line | Display dropdowns on homepage | Done | 100%
154 | Must Have (MVP) | Select Card Options | Tasks to complete | Detail line | Save selected options to Card model | Done | 100%
155 | Must Have (MVP) | Select Card Options | Testing checklist | Section heading | Testing checklist: | Done | 100%
156 | Must Have (MVP) | Select Card Options | Testing checklist | Blank line |  | Not Started | 0%
157 | Must Have (MVP) | Select Card Options | Testing checklist | Detail line | Admin can add recipient types | Done | 100%
158 | Must Have (MVP) | Select Card Options | Testing checklist | Detail line | Admin can add themes | Done | 100%
159 | Must Have (MVP) | Select Card Options | Testing checklist | Detail line | Admin can add colours | Done | 100%
160 | Must Have (MVP) | Select Card Options | Testing checklist | Detail line | Admin can add elements | Done | 100%
161 | Must Have (MVP) | Select Card Options | Testing checklist | Detail line | Dropdowns show correct database values | Done | 100%
162 | Must Have (MVP) | Select Card Options | Testing checklist | Detail line | Selected values save correctly | Done | 100%
163 | Must Have (MVP) | Generate AI Background | Feature heading | Feature heading | Generate AI Background | Done | 100%
164 | Must Have (MVP) | Generate AI Background | User request | Section heading | User request: | Done | 100%
165 | Must Have (MVP) | Generate AI Background | User request | Detail line | As a user, I want to generate a card background using AI so that I do not need design skills. | Done | 100%
166 | Must Have (MVP) | Generate AI Background | User request | Blank line |  | Not Started | 0%
167 | Must Have (MVP) | Generate AI Background | How it can be done | Section heading | How it can be done: | Done | 100%
168 | Must Have (MVP) | Generate AI Background | How it can be done | Detail line | User selects card options and clicks a button. The system sends a prompt to the AI API and saves the generated image. | Done | 100%
169 | Must Have (MVP) | Generate AI Background | How it can be done | Blank line |  | Not Started | 0%
170 | Must Have (MVP) | Generate AI Background | What needs to be included | Section heading | What needs to be included: | Done | 100%
171 | Must Have (MVP) | Generate AI Background | What needs to be included | Blank line |  | Not Started | 0%
172 | Must Have (MVP) | Generate AI Background | What needs to be included | Detail line | Generate background button | Done | 100%
173 | Must Have (MVP) | Generate AI Background | What needs to be included | Detail line | Prompt creation using selected filters | Done | 100%
174 | Must Have (MVP) | Generate AI Background | What needs to be included | Detail line | OpenAI image API integration | Done | 100%
175 | Must Have (MVP) | Generate AI Background | What needs to be included | Detail line | Generated image storage | Done | 100%
176 | Must Have (MVP) | Generate AI Background | What needs to be included | Detail line | Preview display | Done | 100%
177 | Must Have (MVP) | Generate AI Background | What needs to be included | Detail line | Error handling | Done | 100%
178 | Must Have (MVP) | Generate AI Background | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
179 | Must Have (MVP) | Generate AI Background | Tasks to complete | Blank line |  | Not Started | 0%
180 | Must Have (MVP) | Generate AI Background | Tasks to complete | Detail line | Create OpenAI account/API key | Done | 100%
181 | Must Have (MVP) | Generate AI Background | Tasks to complete | Detail line | Store API key in environment variables | Done | 100%
182 | Must Have (MVP) | Generate AI Background | Tasks to complete | Detail line | Create AI background function | Done | 100%
183 | Must Have (MVP) | Generate AI Background | Tasks to complete | Detail line | Build prompt from selected options | Done | 100%
184 | Must Have (MVP) | Generate AI Background | Tasks to complete | Detail line | Call image API | Done | 100%
185 | Must Have (MVP) | Generate AI Background | Tasks to complete | Detail line | Save returned image | Done | 100%
186 | Must Have (MVP) | Generate AI Background | Tasks to complete | Detail line | Link image to Card model | Done | 100%
187 | Must Have (MVP) | Generate AI Background | Tasks to complete | Detail line | Display image in preview | Done | 100%
188 | Must Have (MVP) | Generate AI Background | Tasks to complete | Detail line | Add loading message/spinner | Done | 100%
189 | Must Have (MVP) | Generate AI Background | Tasks to complete | Detail line | Add error message if API fails | Done | 100%
190 | Must Have (MVP) | Generate AI Background | Testing checklist | Section heading | Testing checklist: | Done | 100%
191 | Must Have (MVP) | Generate AI Background | Testing checklist | Blank line |  | Not Started | 0%
192 | Must Have (MVP) | Generate AI Background | Testing checklist | Detail line | Button only triggers when clicked | Done | 100%
193 | Must Have (MVP) | Generate AI Background | Testing checklist | Detail line | Prompt uses selected options | Done | 100%
194 | Must Have (MVP) | Generate AI Background | Testing checklist | Detail line | Image is generated successfully | Done | 100%
195 | Must Have (MVP) | Generate AI Background | Testing checklist | Detail line | Image is saved | Done | 100%
196 | Must Have (MVP) | Generate AI Background | Testing checklist | Detail line | Image appears in preview | Done | 100%
197 | Must Have (MVP) | Generate AI Background | Testing checklist | Detail line | API errors are handled safely | Done | 100%
198 | Must Have (MVP) | Generate AI Background | Testing checklist | Detail line | API key is not exposed in GitHub | Done | 100%
199 | Must Have (MVP) | Add Recipient Name | Feature heading | Feature heading | Add Recipient Name | Done | 100%
200 | Must Have (MVP) | Add Recipient Name | User request | Section heading | User request: | Done | 100%
201 | Must Have (MVP) | Add Recipient Name | User request | Detail line | As a user, I want to optionally add a recipient name so that the card feels personal. | Done | 100%
202 | Must Have (MVP) | Add Recipient Name | User request | Blank line |  | Not Started | 0%
203 | Must Have (MVP) | Add Recipient Name | How it can be done | Section heading | How it can be done: | Done | 100%
204 | Must Have (MVP) | Add Recipient Name | How it can be done | Detail line | User enters a name in an optional field with a character limit. | Done | 100%
205 | Must Have (MVP) | Add Recipient Name | How it can be done | Blank line |  | Not Started | 0%
206 | Must Have (MVP) | Add Recipient Name | What needs to be included | Section heading | What needs to be included: | Done | 100%
207 | Must Have (MVP) | Add Recipient Name | What needs to be included | Blank line |  | Not Started | 0%
208 | Must Have (MVP) | Add Recipient Name | What needs to be included | Detail line | Recipient name field | Done | 100%
209 | Must Have (MVP) | Add Recipient Name | What needs to be included | Detail line | 20 character limit | Done | 100%
210 | Must Have (MVP) | Add Recipient Name | What needs to be included | Detail line | Optional validation | Done | 100%
211 | Must Have (MVP) | Add Recipient Name | What needs to be included | Detail line | Character counter | Done | 100%
212 | Must Have (MVP) | Add Recipient Name | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
213 | Must Have (MVP) | Add Recipient Name | Tasks to complete | Blank line |  | Not Started | 0%
214 | Must Have (MVP) | Add Recipient Name | Tasks to complete | Detail line | Add recipient_name field to Card model | Done | 100%
215 | Must Have (MVP) | Add Recipient Name | Tasks to complete | Detail line | Set max length to 20 | Done | 100%
216 | Must Have (MVP) | Add Recipient Name | Tasks to complete | Detail line | Add input field to form | Done | 100%
217 | Must Have (MVP) | Add Recipient Name | Tasks to complete | Detail line | Add frontend character counter | Done | 100%
218 | Must Have (MVP) | Add Recipient Name | Tasks to complete | Detail line | Add optional validation | Done | 100%
219 | Must Have (MVP) | Add Recipient Name | Tasks to complete | Detail line | Display name on preview if entered | Done | 100%
220 | Must Have (MVP) | Add Recipient Name | Testing checklist | Section heading | Testing checklist: | Done | 100%
221 | Must Have (MVP) | Add Recipient Name | Testing checklist | Blank line |  | Not Started | 0%
222 | Must Have (MVP) | Add Recipient Name | Testing checklist | Detail line | Name field accepts text | Done | 100%
223 | Must Have (MVP) | Add Recipient Name | Testing checklist | Detail line | Name field can be left empty | Done | 100%
224 | Must Have (MVP) | Add Recipient Name | Testing checklist | Detail line | Counter updates correctly | Done | 100%
225 | Must Have (MVP) | Add Recipient Name | Testing checklist | Detail line | More than 20 characters cannot be entered | Done | 100%
226 | Must Have (MVP) | Add Recipient Name | Testing checklist | Detail line | Name appears in preview when provided | Done | 100%
227 | Must Have (MVP) | Add / Generate / Improve Message | Feature heading | Feature heading | Add / Generate / Improve Message | Done | 100%
228 | Must Have (MVP) | Add / Generate / Improve Message | User request | Section heading | User request: | Done | 100%
229 | Must Have (MVP) | Add / Generate / Improve Message | User request | Detail line | As a user, I want to write, generate, or improve a short thank-you message so that my card sounds personal and polished. | Done | 100%
230 | Must Have (MVP) | Add / Generate / Improve Message | User request | Blank line |  | Not Started | 0%
231 | Must Have (MVP) | Add / Generate / Improve Message | How it can be done | Section heading | How it can be done: | Done | 100%
232 | Must Have (MVP) | Add / Generate / Improve Message | How it can be done | Detail line | User writes a message manually or clicks an AI button. If the field is empty, AI generates a new message. If text exists, AI improves it. | Done | 100%
233 | Must Have (MVP) | Add / Generate / Improve Message | How it can be done | Blank line |  | Not Started | 0%
234 | Must Have (MVP) | Add / Generate / Improve Message | What needs to be included | Section heading | What needs to be included: | Done | 100%
235 | Must Have (MVP) | Add / Generate / Improve Message | What needs to be included | Blank line |  | Not Started | 0%
236 | Must Have (MVP) | Add / Generate / Improve Message | What needs to be included | Detail line | Message textarea | Done | 100%
237 | Must Have (MVP) | Add / Generate / Improve Message | What needs to be included | Detail line | 150 character limit | Done | 100%
238 | Must Have (MVP) | Add / Generate / Improve Message | What needs to be included | Detail line | Character counter | Done | 100%
239 | Must Have (MVP) | Add / Generate / Improve Message | What needs to be included | Detail line | Generate / Improve AI button | Done | 100%
240 | Must Have (MVP) | Add / Generate / Improve Message | What needs to be included | Detail line | OpenAI text API integration | Done | 100%
241 | Must Have (MVP) | Add / Generate / Improve Message | What needs to be included | Detail line | Message saved to card | Done | 100%
242 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
243 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Blank line |  | Not Started | 0%
244 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Detail line | Add message field to Card model | Done | 100%
245 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Detail line | Set max length to 150 | Done | 100%
246 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Detail line | Add textarea to template | Done | 100%
247 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Detail line | Add character counter | Done | 100%
248 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Detail line | Create AI message function | Done | 100%
249 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Detail line | Detect whether message field is empty | Done | 100%
250 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Detail line | If empty, generate new message | Done | 100%
251 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Detail line | If filled, improve existing message | Done | 100%
252 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Detail line | Save returned AI text | Done | 100%
253 | Must Have (MVP) | Add / Generate / Improve Message | Tasks to complete | Detail line | Display updated message in preview | Done | 100%
254 | Must Have (MVP) | Add / Generate / Improve Message | Testing checklist | Section heading | Testing checklist: | Done | 100%
255 | Must Have (MVP) | Add / Generate / Improve Message | Testing checklist | Blank line |  | Not Started | 0%
256 | Must Have (MVP) | Add / Generate / Improve Message | Testing checklist | Detail line | User can type message manually | Done | 100%
257 | Must Have (MVP) | Add / Generate / Improve Message | Testing checklist | Detail line | Counter updates correctly | Done | 100%
258 | Must Have (MVP) | Add / Generate / Improve Message | Testing checklist | Detail line | Message cannot exceed 150 characters | Done | 100%
259 | Must Have (MVP) | Add / Generate / Improve Message | Testing checklist | Detail line | Empty field generates new AI message | Done | 100%
260 | Must Have (MVP) | Add / Generate / Improve Message | Testing checklist | Detail line | Existing message is improved by AI | Done | 100%
261 | Must Have (MVP) | Add / Generate / Improve Message | Testing checklist | Detail line | AI message stays within limit | Done | 100%
262 | Must Have (MVP) | Add / Generate / Improve Message | Testing checklist | Detail line | Message appears in preview | Done | 100%
263 | Must Have (MVP) | No Message Option | Feature heading | Feature heading | No Message Option | Done | 100%
264 | Must Have (MVP) | No Message Option | User request | Section heading | User request: | Done | 100%
265 | Must Have (MVP) | No Message Option | User request | Detail line | As a user, I want to create a card without a message so that I have flexibility. | Done | 100%
266 | Must Have (MVP) | No Message Option | User request | Blank line |  | Not Started | 0%
267 | Must Have (MVP) | No Message Option | How it can be done | Section heading | How it can be done: | Done | 100%
268 | Must Have (MVP) | No Message Option | How it can be done | Detail line | User ticks a checkbox to confirm the card should have no message. | Done | 100%
269 | Must Have (MVP) | No Message Option | How it can be done | Blank line |  | Not Started | 0%
270 | Must Have (MVP) | No Message Option | What needs to be included | Section heading | What needs to be included: | Done | 100%
271 | Must Have (MVP) | No Message Option | What needs to be included | Blank line |  | Not Started | 0%
272 | Must Have (MVP) | No Message Option | What needs to be included | Detail line | No message checkbox | Done | 100%
273 | Must Have (MVP) | No Message Option | What needs to be included | Detail line | Disabled/hid message field when selected | Done | 100%
274 | Must Have (MVP) | No Message Option | What needs to be included | Detail line | Saved no_message value | Done | 100%
275 | Must Have (MVP) | No Message Option | What needs to be included | Detail line | Background prompt adjusted for no message design | Done | 100%
276 | Must Have (MVP) | No Message Option | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
277 | Must Have (MVP) | No Message Option | Tasks to complete | Blank line |  | Not Started | 0%
278 | Must Have (MVP) | No Message Option | Tasks to complete | Detail line | Add no_message BooleanField to Card model | Done | 100%
279 | Must Have (MVP) | No Message Option | Tasks to complete | Detail line | Add checkbox to form | Done | 100%
280 | Must Have (MVP) | No Message Option | Tasks to complete | Detail line | Add JavaScript to hide/disable message area | Done | 100%
281 | Must Have (MVP) | No Message Option | Tasks to complete | Detail line | Disable AI message button when checked | Done | 100%
282 | Must Have (MVP) | No Message Option | Tasks to complete | Detail line | Adjust AI background prompt if no message is selected | Done | 100%
283 | Must Have (MVP) | No Message Option | Tasks to complete | Detail line | Save no message choice | Done | 100%
284 | Must Have (MVP) | No Message Option | Testing checklist | Section heading | Testing checklist: | Done | 100%
285 | Must Have (MVP) | No Message Option | Testing checklist | Blank line |  | Not Started | 0%
286 | Must Have (MVP) | No Message Option | Testing checklist | Detail line | Checkbox can be selected | Done | 100%
287 | Must Have (MVP) | No Message Option | Testing checklist | Detail line | Message field hides or disables | Done | 100%
288 | Must Have (MVP) | No Message Option | Testing checklist | Detail line | AI message button disables | Done | 100%
289 | Must Have (MVP) | No Message Option | Testing checklist | Detail line | Card can be saved without message | Done | 100%
290 | Must Have (MVP) | No Message Option | Testing checklist | Detail line | Preview works without message | Done | 100%
291 | Must Have (MVP) | Preview Card Before Payment | Feature heading | Feature heading | Preview Card Before Payment | Done | 100%
292 | Must Have (MVP) | Preview Card Before Payment | User request | Section heading | User request: | Done | 100%
293 | Must Have (MVP) | Preview Card Before Payment | User request | Detail line | As a user, I want to preview my card before payment so that I can confirm it looks correct. | Done | 100%
294 | Must Have (MVP) | Preview Card Before Payment | User request | Blank line |  | Not Started | 0%
295 | Must Have (MVP) | Preview Card Before Payment | How it can be done | Section heading | How it can be done: | Done | 100%
296 | Must Have (MVP) | Preview Card Before Payment | How it can be done | Detail line | User clicks preview or update preview to see the current background, name, and message. | Done | 100%
297 | Must Have (MVP) | Preview Card Before Payment | How it can be done | Blank line |  | Not Started | 0%
298 | Must Have (MVP) | Preview Card Before Payment | What needs to be included | Section heading | What needs to be included: | Done | 100%
299 | Must Have (MVP) | Preview Card Before Payment | What needs to be included | Blank line |  | Not Started | 0%
300 | Must Have (MVP) | Preview Card Before Payment | What needs to be included | Detail line | Preview area | Done | 100%
301 | Must Have (MVP) | Preview Card Before Payment | What needs to be included | Detail line | Update preview button | Done | 100%
302 | Must Have (MVP) | Preview Card Before Payment | What needs to be included | Detail line | Preview page or section | Done | 100%
303 | Must Have (MVP) | Preview Card Before Payment | What needs to be included | Detail line | Background image display | Done | 100%
304 | Must Have (MVP) | Preview Card Before Payment | What needs to be included | Detail line | Message/name display | Done | 100%
305 | Must Have (MVP) | Preview Card Before Payment | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
306 | Must Have (MVP) | Preview Card Before Payment | Tasks to complete | Blank line |  | Not Started | 0%
307 | Must Have (MVP) | Preview Card Before Payment | Tasks to complete | Detail line | Create preview layout | Done | 100%
308 | Must Have (MVP) | Preview Card Before Payment | Tasks to complete | Detail line | Display generated background | Done | 100%
309 | Must Have (MVP) | Preview Card Before Payment | Tasks to complete | Detail line | Overlay or display recipient name | Done | 100%
310 | Must Have (MVP) | Preview Card Before Payment | Tasks to complete | Detail line | Overlay or display message | Done | 100%
311 | Must Have (MVP) | Preview Card Before Payment | Tasks to complete | Detail line | Create update preview button | Done | 100%
312 | Must Have (MVP) | Preview Card Before Payment | Tasks to complete | Detail line | Create preview view/page if needed | Done | 100%
313 | Must Have (MVP) | Preview Card Before Payment | Tasks to complete | Detail line | Add preview button from basket/account | Done | 100%
314 | Must Have (MVP) | Preview Card Before Payment | Testing checklist | Section heading | Testing checklist: | Done | 100%
315 | Must Have (MVP) | Preview Card Before Payment | Testing checklist | Blank line |  | Not Started | 0%
316 | Must Have (MVP) | Preview Card Before Payment | Testing checklist | Detail line | Preview shows background image | Done | 100%
317 | Must Have (MVP) | Preview Card Before Payment | Testing checklist | Detail line | Preview shows message if provided | Done | 100%
318 | Must Have (MVP) | Preview Card Before Payment | Testing checklist | Detail line | Preview works without message | Done | 100%
319 | Must Have (MVP) | Preview Card Before Payment | Testing checklist | Detail line | Preview updates after changes | Done | 100%
320 | Must Have (MVP) | Preview Card Before Payment | Testing checklist | Detail line | User can preview before adding to basket/payment | Done | 100%
321 | Must Have (MVP) | Save Card | Feature heading | Feature heading | Save Card | Done | 100%
322 | Must Have (MVP) | Save Card | User request | Section heading | User request: | Done | 100%
323 | Must Have (MVP) | Save Card | User request | Detail line | As a logged-in user, I want to save my card so that I can continue editing it later. | Done | 100%
324 | Must Have (MVP) | Save Card | User request | Blank line |  | Not Started | 0%
325 | Must Have (MVP) | Save Card | How it can be done | Section heading | How it can be done: | Done | 100%
326 | Must Have (MVP) | Save Card | How it can be done | Detail line | User clicks save and the card is stored as an unpaid draft linked to their account. | Done | 100%
327 | Must Have (MVP) | Save Card | How it can be done | Blank line |  | Not Started | 0%
328 | Must Have (MVP) | Save Card | What needs to be included | Section heading | What needs to be included: | Done | 100%
329 | Must Have (MVP) | Save Card | What needs to be included | Blank line |  | Not Started | 0%
330 | Must Have (MVP) | Save Card | What needs to be included | Detail line | Save button | Done | 100%
331 | Must Have (MVP) | Save Card | What needs to be included | Detail line | Card model | Done | 100%
332 | Must Have (MVP) | Save Card | What needs to be included | Detail line | User relationship | Done | 100%
333 | Must Have (MVP) | Save Card | What needs to be included | Detail line | Draft state | Done | 100%
334 | Must Have (MVP) | Save Card | What needs to be included | Detail line | Redirect or success message | Done | 100%
335 | Must Have (MVP) | Save Card | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
336 | Must Have (MVP) | Save Card | Tasks to complete | Blank line |  | Not Started | 0%
337 | Must Have (MVP) | Save Card | Tasks to complete | Detail line | Create Card model | Done | 100%
338 | Must Have (MVP) | Save Card | Tasks to complete | Detail line | Add foreign key to User | Done | 100%
339 | Must Have (MVP) | Save Card | Tasks to complete | Detail line | Add is_paid field default False | Done | 100%
340 | Must Have (MVP) | Save Card | Tasks to complete | Detail line | Add save card view logic | Done | 100%
341 | Must Have (MVP) | Save Card | Tasks to complete | Detail line | Link saved card to logged-in user | Done | 100%
342 | Must Have (MVP) | Save Card | Tasks to complete | Detail line | Show success message | Done | 100%
343 | Must Have (MVP) | Save Card | Tasks to complete | Detail line | Redirect to account or keep user on form | Done | 100%
344 | Must Have (MVP) | Save Card | Testing checklist | Section heading | Testing checklist: | Done | 100%
345 | Must Have (MVP) | Save Card | Testing checklist | Blank line |  | Not Started | 0%
346 | Must Have (MVP) | Save Card | Testing checklist | Detail line | Logged-in user can save card | Done | 100%
347 | Must Have (MVP) | Save Card | Testing checklist | Detail line | Saved card appears in account page | Done | 100%
348 | Must Have (MVP) | Save Card | Testing checklist | Detail line | Saved card belongs to correct user | Done | 100%
349 | Must Have (MVP) | Save Card | Testing checklist | Detail line | Anonymous user cannot save card | Done | 100%
350 | Must Have (MVP) | Save Card | Testing checklist | Detail line | Success message appears | Done | 100%
351 | Must Have (MVP) | Edit Saved Card | Feature heading | Feature heading | Edit Saved Card | Done | 100%
352 | Must Have (MVP) | Edit Saved Card | User request | Section heading | User request: | Done | 100%
353 | Must Have (MVP) | Edit Saved Card | User request | Detail line | As a logged-in user, I want to edit a saved card so that I can improve it before purchase. | Done | 100%
354 | Must Have (MVP) | Edit Saved Card | User request | Blank line |  | Not Started | 0%
355 | Must Have (MVP) | Edit Saved Card | How it can be done | Section heading | How it can be done: | Done | 100%
356 | Must Have (MVP) | Edit Saved Card | How it can be done | Detail line | User opens a saved card from the account page and updates its details. | Done | 100%
357 | Must Have (MVP) | Edit Saved Card | How it can be done | Blank line |  | Not Started | 0%
358 | Must Have (MVP) | Edit Saved Card | What needs to be included | Section heading | What needs to be included: | Done | 100%
359 | Must Have (MVP) | Edit Saved Card | What needs to be included | Blank line |  | Not Started | 0%
360 | Must Have (MVP) | Edit Saved Card | What needs to be included | Detail line | Edit button | Done | 100%
361 | Must Have (MVP) | Edit Saved Card | What needs to be included | Detail line | Edit card view | Done | 100%
362 | Must Have (MVP) | Edit Saved Card | What needs to be included | Detail line | Pre-filled form | Done | 100%
363 | Must Have (MVP) | Edit Saved Card | What needs to be included | Detail line | Permission checks | Done | 100%
364 | Must Have (MVP) | Edit Saved Card | What needs to be included | Detail line | Prevent editing paid cards | Done | 100%
365 | Must Have (MVP) | Edit Saved Card | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
366 | Must Have (MVP) | Edit Saved Card | Tasks to complete | Blank line |  | Not Started | 0%
367 | Must Have (MVP) | Edit Saved Card | Tasks to complete | Detail line | Create edit card URL | Done | 100%
368 | Must Have (MVP) | Edit Saved Card | Tasks to complete | Detail line | Create edit card view | Done | 100%
369 | Must Have (MVP) | Edit Saved Card | Tasks to complete | Detail line | Load existing card data into form | Done | 100%
370 | Must Have (MVP) | Edit Saved Card | Tasks to complete | Detail line | Save updated values | Done | 100%
371 | Must Have (MVP) | Edit Saved Card | Tasks to complete | Detail line | Check card belongs to logged-in user | Done | 100%
372 | Must Have (MVP) | Edit Saved Card | Tasks to complete | Detail line | Prevent editing if card is paid | Done | 100%
373 | Must Have (MVP) | Edit Saved Card | Tasks to complete | Detail line | Add success message after edit | Done | 100%
374 | Must Have (MVP) | Edit Saved Card | Testing checklist | Section heading | Testing checklist: | Done | 100%
375 | Must Have (MVP) | Edit Saved Card | Testing checklist | Blank line |  | Not Started | 0%
376 | Must Have (MVP) | Edit Saved Card | Testing checklist | Detail line | Saved card opens in edit mode | Done | 100%
377 | Must Have (MVP) | Edit Saved Card | Testing checklist | Detail line | Form is pre-filled | Done | 100%
378 | Must Have (MVP) | Edit Saved Card | Testing checklist | Detail line | User can update card details | Done | 100%
379 | Must Have (MVP) | Edit Saved Card | Testing checklist | Detail line | Updated card saves correctly | Done | 100%
380 | Must Have (MVP) | Edit Saved Card | Testing checklist | Detail line | User cannot edit another user’s card | Done | 100%
381 | Must Have (MVP) | Edit Saved Card | Testing checklist | Detail line | Paid card cannot be edited | Done | 100%
382 | Must Have (MVP) | Delete Saved Card | Feature heading | Feature heading | Delete Saved Card | Done | 100%
383 | Must Have (MVP) | Delete Saved Card | User request | Section heading | User request: | Done | 100%
384 | Must Have (MVP) | Delete Saved Card | User request | Detail line | As a logged-in user, I want to delete saved cards I no longer want so that my account stays organised. | Done | 100%
385 | Must Have (MVP) | Delete Saved Card | User request | Blank line |  | Not Started | 0%
386 | Must Have (MVP) | Delete Saved Card | How it can be done | Section heading | How it can be done: | Done | 100%
387 | Must Have (MVP) | Delete Saved Card | How it can be done | Detail line | User clicks delete on a saved card and confirms the action. | Done | 100%
388 | Must Have (MVP) | Delete Saved Card | How it can be done | Blank line |  | Not Started | 0%
389 | Must Have (MVP) | Delete Saved Card | What needs to be included | Section heading | What needs to be included: | Done | 100%
390 | Must Have (MVP) | Delete Saved Card | What needs to be included | Blank line |  | Not Started | 0%
391 | Must Have (MVP) | Delete Saved Card | What needs to be included | Detail line | Delete button | Done | 100%
392 | Must Have (MVP) | Delete Saved Card | What needs to be included | Detail line | Confirmation step | Done | 100%
393 | Must Have (MVP) | Delete Saved Card | What needs to be included | Detail line | Delete view | Done | 100%
394 | Must Have (MVP) | Delete Saved Card | What needs to be included | Detail line | Permission checks | Done | 100%
395 | Must Have (MVP) | Delete Saved Card | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
396 | Must Have (MVP) | Delete Saved Card | Tasks to complete | Blank line |  | Not Started | 0%
397 | Must Have (MVP) | Delete Saved Card | Tasks to complete | Detail line | Create delete card URL | Done | 100%
398 | Must Have (MVP) | Delete Saved Card | Tasks to complete | Detail line | Create delete view | Done | 100%
399 | Must Have (MVP) | Delete Saved Card | Tasks to complete | Detail line | Add confirmation page or modal | Done | 100%
400 | Must Have (MVP) | Delete Saved Card | Tasks to complete | Detail line | Check card belongs to logged-in user | Done | 100%
401 | Must Have (MVP) | Delete Saved Card | Tasks to complete | Detail line | Prevent deleting paid cards if needed | Done | 100%
402 | Must Have (MVP) | Delete Saved Card | Tasks to complete | Detail line | Redirect after deletion | Done | 100%
403 | Must Have (MVP) | Delete Saved Card | Tasks to complete | Detail line | Show success message | Done | 100%
404 | Must Have (MVP) | Delete Saved Card | Testing checklist | Section heading | Testing checklist: | Done | 100%
405 | Must Have (MVP) | Delete Saved Card | Testing checklist | Blank line |  | Not Started | 0%
406 | Must Have (MVP) | Delete Saved Card | Testing checklist | Detail line | Delete button appears for saved cards | Done | 100%
407 | Must Have (MVP) | Delete Saved Card | Testing checklist | Detail line | Confirmation is shown | Done | 100%
408 | Must Have (MVP) | Delete Saved Card | Testing checklist | Detail line | Card is removed after confirmation | Done | 100%
409 | Must Have (MVP) | Delete Saved Card | Testing checklist | Detail line | User cannot delete another user’s card | Done | 100%
410 | Must Have (MVP) | Delete Saved Card | Testing checklist | Detail line | Purchased cards are not accidentally deleted | Done | 100%
411 | Must Have (MVP) | Account Page | Feature heading | Feature heading | Account Page | Done | 100%
412 | Must Have (MVP) | Account Page | User request | Section heading | User request: | Done | 100%
413 | Must Have (MVP) | Account Page | User request | Detail line | As a logged-in user, I want an account page where I can view saved and purchased cards. | Done | 100%
414 | Must Have (MVP) | Account Page | User request | Blank line |  | Not Started | 0%
415 | Must Have (MVP) | Account Page | How it can be done | Section heading | How it can be done: | Done | 100%
416 | Must Have (MVP) | Account Page | How it can be done | Detail line | User opens their account page and sees separate sections for drafts and purchased cards. | Done | 100%
417 | Must Have (MVP) | Account Page | How it can be done | Blank line |  | Not Started | 0%
418 | Must Have (MVP) | Account Page | What needs to be included | Section heading | What needs to be included: | Done | 100%
419 | Must Have (MVP) | Account Page | What needs to be included | Blank line |  | Not Started | 0%
420 | Must Have (MVP) | Account Page | What needs to be included | Detail line | Account page | Done | 100%
421 | Must Have (MVP) | Account Page | What needs to be included | Detail line | Saved cards section | Done | 100%
422 | Must Have (MVP) | Account Page | What needs to be included | Detail line | Purchased cards section | Done | 100%
423 | Must Have (MVP) | Account Page | What needs to be included | Detail line | Preview/Edit/Delete/Add to basket buttons for drafts | Done | 100%
424 | Must Have (MVP) | Account Page | What needs to be included | Detail line | Download button for purchased cards | Done | 100%
425 | Must Have (MVP) | Account Page | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
426 | Must Have (MVP) | Account Page | Tasks to complete | Blank line |  | Not Started | 0%
427 | Must Have (MVP) | Account Page | Tasks to complete | Detail line | Create account URL | Done | 100%
428 | Must Have (MVP) | Account Page | Tasks to complete | Detail line | Create account view | Done | 100%
429 | Must Have (MVP) | Account Page | Tasks to complete | Detail line | Filter user cards by is_paid=False | Done | 100%
430 | Must Have (MVP) | Account Page | Tasks to complete | Detail line | Filter user cards by is_paid=True | Done | 100%
431 | Must Have (MVP) | Account Page | Tasks to complete | Detail line | Display saved cards | Done | 100%
432 | Must Have (MVP) | Account Page | Tasks to complete | Detail line | Display purchased cards | Done | 100%
433 | Must Have (MVP) | Account Page | Tasks to complete | Detail line | Add buttons for each card state | Done | 100%
434 | Must Have (MVP) | Account Page | Tasks to complete | Detail line | Add empty state messages | Done | 100%
435 | Must Have (MVP) | Account Page | Testing checklist | Section heading | Testing checklist: | Done | 100%
436 | Must Have (MVP) | Account Page | Testing checklist | Blank line |  | Not Started | 0%
437 | Must Have (MVP) | Account Page | Testing checklist | Detail line | Account page requires login | Done | 100%
438 | Must Have (MVP) | Account Page | Testing checklist | Detail line | Saved cards appear in saved section | Done | 100%
439 | Must Have (MVP) | Account Page | Testing checklist | Detail line | Purchased cards appear in purchased section | Done | 100%
440 | Must Have (MVP) | Account Page | Testing checklist | Detail line | Empty messages display correctly | Done | 100%
441 | Must Have (MVP) | Account Page | Testing checklist | Detail line | User only sees their own cards | Done | 100%
442 | Must Have (MVP) | Basket Page | Feature heading | Feature heading | Basket Page | Done | 100%
443 | Must Have (MVP) | Basket Page | User request | Section heading | User request: | Done | 100%
444 | Must Have (MVP) | Basket Page | User request | Detail line | As a user, I want to add a card to my basket so that I can purchase it. | Done | 100%
445 | Must Have (MVP) | Basket Page | User request | Blank line |  | Not Started | 0%
446 | Must Have (MVP) | Basket Page | How it can be done | Section heading | How it can be done: | Done | 100%
447 | Must Have (MVP) | Basket Page | How it can be done | Detail line | User clicks add to basket and reviews the selected card before checkout. | Done | 100%
448 | Must Have (MVP) | Basket Page | How it can be done | Blank line |  | Not Started | 0%
449 | Must Have (MVP) | Basket Page | What needs to be included | Section heading | What needs to be included: | Done | 100%
450 | Must Have (MVP) | Basket Page | What needs to be included | Blank line |  | Not Started | 0%
451 | Must Have (MVP) | Basket Page | What needs to be included | Detail line | Basket page | Done | 100%
452 | Must Have (MVP) | Basket Page | What needs to be included | Detail line | Add to basket button | Done | 100%
453 | Must Have (MVP) | Basket Page | What needs to be included | Detail line | Basket item display | Done | 100%
454 | Must Have (MVP) | Basket Page | What needs to be included | Detail line | Fixed price | Done | 100%
455 | Must Have (MVP) | Basket Page | What needs to be included | Detail line | Remove from basket option | Done | 100%
456 | Must Have (MVP) | Basket Page | What needs to be included | Detail line | Checkout button | Done | 100%
457 | Must Have (MVP) | Basket Page | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
458 | Must Have (MVP) | Basket Page | Tasks to complete | Blank line |  | Not Started | 0%
459 | Must Have (MVP) | Basket Page | Tasks to complete | Detail line | Create orders app | Done | 100%
460 | Must Have (MVP) | Basket Page | Tasks to complete | Detail line | Create Order model | Done | 100%
461 | Must Have (MVP) | Basket Page | Tasks to complete | Detail line | Create OrderItem model | Done | 100%
462 | Must Have (MVP) | Basket Page | Tasks to complete | Detail line | Add basket URL | Done | 100%
463 | Must Have (MVP) | Basket Page | Tasks to complete | Detail line | Create add to basket view | Done | 100%
464 | Must Have (MVP) | Basket Page | Tasks to complete | Detail line | Create basket template | Done | 100%
465 | Must Have (MVP) | Basket Page | Tasks to complete | Detail line | Display selected card | Done | 100%
466 | Must Have (MVP) | Basket Page | Tasks to complete | Detail line | Display fixed price | Done | 100%
467 | Must Have (MVP) | Basket Page | Tasks to complete | Detail line | Add remove button | Done | 100%
468 | Must Have (MVP) | Basket Page | Tasks to complete | Detail line | Add checkout button | Done | 100%
469 | Must Have (MVP) | Basket Page | Testing checklist | Section heading | Testing checklist: | Done | 100%
470 | Must Have (MVP) | Basket Page | Testing checklist | Blank line |  | Not Started | 0%
471 | Must Have (MVP) | Basket Page | Testing checklist | Detail line | Card can be added to basket | Done | 100%
472 | Must Have (MVP) | Basket Page | Testing checklist | Detail line | Basket shows correct card | Done | 100%
473 | Must Have (MVP) | Basket Page | Testing checklist | Detail line | Price displays correctly | Done | 100%
474 | Must Have (MVP) | Basket Page | Testing checklist | Detail line | Card can be removed from basket | Done | 100%
475 | Must Have (MVP) | Basket Page | Testing checklist | Detail line | Basket does not show other users’ cards | Done | 100%
476 | Must Have (MVP) | Payment / Checkout | Feature heading | Feature heading | Payment / Checkout | Done | 100%
477 | Must Have (MVP) | Payment / Checkout | User request | Section heading | User request: | Done | 100%
478 | Must Have (MVP) | Payment / Checkout | User request | Detail line | As a user, I want to complete a payment so that I can finalise my card. | Done | 100%
479 | Must Have (MVP) | Payment / Checkout | User request | Blank line |  | Not Started | 0%
480 | Must Have (MVP) | Payment / Checkout | How it can be done | Section heading | How it can be done: | Done | 100%
481 | Must Have (MVP) | Payment / Checkout | How it can be done | Detail line | User completes a Stripe test checkout and the card becomes purchased after successful payment. | Done | 100%
482 | Must Have (MVP) | Payment / Checkout | How it can be done | Blank line |  | Not Started | 0%
483 | Must Have (MVP) | Payment / Checkout | What needs to be included | Section heading | What needs to be included: | Done | 100%
484 | Must Have (MVP) | Payment / Checkout | What needs to be included | Blank line |  | Not Started | 0%
485 | Must Have (MVP) | Payment / Checkout | What needs to be included | Detail line | Stripe test mode | Done | 100%
486 | Must Have (MVP) | Payment / Checkout | What needs to be included | Detail line | Checkout button | Done | 100%
487 | Must Have (MVP) | Payment / Checkout | What needs to be included | Detail line | Success page | Done | 100%
488 | Must Have (MVP) | Payment / Checkout | What needs to be included | Detail line | Cancel page | Done | 100%
489 | Must Have (MVP) | Payment / Checkout | What needs to be included | Detail line | Mark card/order as paid | Done | 100%
490 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
491 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Blank line |  | Not Started | 0%
492 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Detail line | Create Stripe account | Done | 100%
493 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Detail line | Add Stripe test keys to environment variables | Done | 100%
494 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Detail line | Install Stripe package | Done | 100%
495 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Detail line | Create checkout session view | Done | 100%
496 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Detail line | Send card/order details to Stripe | Done | 100%
497 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Detail line | Create success URL | Done | 100%
498 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Detail line | Create cancel URL | Done | 100%
499 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Detail line | Mark card as paid after successful checkout | Done | 100%
500 | Must Have (MVP) | Payment / Checkout | Tasks to complete | Detail line | Generate PDF after payment or before download | Done | 100%
501 | Must Have (MVP) | Payment / Checkout | Testing checklist | Section heading | Testing checklist: | Done | 100%
502 | Must Have (MVP) | Payment / Checkout | Testing checklist | Blank line |  | Not Started | 0%
503 | Must Have (MVP) | Payment / Checkout | Testing checklist | Detail line | Checkout opens in Stripe test mode | Done | 100%
504 | Must Have (MVP) | Payment / Checkout | Testing checklist | Detail line | Test card payment succeeds | Done | 100%
505 | Must Have (MVP) | Payment / Checkout | Testing checklist | Detail line | Cancel flow works | Done | 100%
506 | Must Have (MVP) | Payment / Checkout | Testing checklist | Detail line | Card becomes paid after successful payment | Done | 100%
507 | Must Have (MVP) | Payment / Checkout | Testing checklist | Detail line | Paid card appears in purchased section | Done | 100%
508 | Must Have (MVP) | Payment / Checkout | Testing checklist | Detail line | Stripe keys are not pushed to GitHub | Done | 100%
509 | Must Have (MVP) | Download PDF | Feature heading | Feature heading | Download PDF | Done | 100%
510 | Must Have (MVP) | Download PDF | User request | Section heading | User request: | Done | 100%
511 | Must Have (MVP) | Download PDF | User request | Detail line | As a user, I want to download my purchased card as a PDF so that I can use or share it. | Done | 100%
512 | Must Have (MVP) | Download PDF | User request | Blank line |  | Not Started | 0%
513 | Must Have (MVP) | Download PDF | How it can be done | Section heading | How it can be done: | Done | 100%
514 | Must Have (MVP) | Download PDF | How it can be done | Detail line | After payment, the system generates a PDF and provides a download link. | Done | 100%
515 | Must Have (MVP) | Download PDF | How it can be done | Blank line |  | Not Started | 0%
516 | Must Have (MVP) | Download PDF | What needs to be included | Section heading | What needs to be included: | Done | 100%
517 | Must Have (MVP) | Download PDF | What needs to be included | Blank line |  | Not Started | 0%
518 | Must Have (MVP) | Download PDF | What needs to be included | Detail line | PDF generation | Done | 100%
519 | Must Have (MVP) | Download PDF | What needs to be included | Detail line | PDF file storage | Done | 100%
520 | Must Have (MVP) | Download PDF | What needs to be included | Detail line | Download button | Done | 100%
521 | Must Have (MVP) | Download PDF | What needs to be included | Detail line | Permission checks | Done | 100%
522 | Must Have (MVP) | Download PDF | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
523 | Must Have (MVP) | Download PDF | Tasks to complete | Blank line |  | Not Started | 0%
524 | Must Have (MVP) | Download PDF | Tasks to complete | Detail line | Choose PDF library | Done | 100%
525 | Must Have (MVP) | Download PDF | Tasks to complete | Detail line | Create PDF generation function | Done | 100%
526 | Must Have (MVP) | Download PDF | Tasks to complete | Detail line | Add background image to PDF | Done | 100%
527 | Must Have (MVP) | Download PDF | Tasks to complete | Detail line | Add recipient name/message to PDF | Done | 100%
528 | Must Have (MVP) | Download PDF | Tasks to complete | Detail line | Save PDF to Card model | Done | 100%
529 | Must Have (MVP) | Download PDF | Tasks to complete | Detail line | Create download view | Done | 100%
530 | Must Have (MVP) | Download PDF | Tasks to complete | Detail line | Add download button to account page | Done | 100%
531 | Must Have (MVP) | Download PDF | Tasks to complete | Detail line | Restrict download to owner | Done | 100%
532 | Must Have (MVP) | Download PDF | Tasks to complete | Detail line | Restrict download to paid cards | Done | 100%
533 | Must Have (MVP) | Download PDF | Testing checklist | Section heading | Testing checklist: | Done | 100%
534 | Must Have (MVP) | Download PDF | Testing checklist | Blank line |  | Not Started | 0%
535 | Must Have (MVP) | Download PDF | Testing checklist | Detail line | PDF generates successfully | Done | 100%
536 | Must Have (MVP) | Download PDF | Testing checklist | Detail line | PDF includes correct background | Done | 100%
537 | Must Have (MVP) | Download PDF | Testing checklist | Detail line | PDF includes message if provided | Done | 100%
538 | Must Have (MVP) | Download PDF | Testing checklist | Detail line | PDF works without message | Done | 100%
539 | Must Have (MVP) | Download PDF | Testing checklist | Detail line | Only paid cards can be downloaded | Done | 100%
540 | Must Have (MVP) | Download PDF | Testing checklist | Detail line | User cannot download another user’s card | Done | 100%
541 | Should Have |  | Priority heading | Priority heading | Should Have | Done | 100%
542 | Should Have | Fixed Price Per Card | Feature heading | Feature heading | Fixed Price Per Card | Done | 100%
543 | Should Have | Fixed Price Per Card | User request | Section heading | User request: | Done | 100%
544 | Should Have | Fixed Price Per Card | User request | Detail line | As a user, I want to see one clear price so that I understand the cost before checkout. | Done | 100%
545 | Should Have | Fixed Price Per Card | User request | Blank line |  |  | 0%
546 | Should Have | Fixed Price Per Card | How it can be done | Section heading | How it can be done: | Done | 100%
547 | Should Have | Fixed Price Per Card | How it can be done | Detail line | The system uses one fixed price for all cards. | Done | 100%
548 | Should Have | Fixed Price Per Card | How it can be done | Blank line |  |  | 0%
549 | Should Have | Fixed Price Per Card | What needs to be included | Section heading | What needs to be included: | Done | 100%
550 | Should Have | Fixed Price Per Card | What needs to be included | Blank line |  |  | 0%
551 | Should Have | Fixed Price Per Card | What needs to be included | Detail line | Fixed price display | Done | 100%
552 | Should Have | Fixed Price Per Card | What needs to be included | Detail line | Backend price constant or model field | Done | 100%
553 | Should Have | Fixed Price Per Card | What needs to be included | Detail line | Basket total | Done | 100%
554 | Should Have | Fixed Price Per Card | What needs to be included | Detail line | Checkout amount | Done | 100%
555 | Should Have | Fixed Price Per Card | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
556 | Should Have | Fixed Price Per Card | Tasks to complete | Blank line |  |  | 0%
557 | Should Have | Fixed Price Per Card | Tasks to complete | Detail line | Decide card price | Done | 100%
558 | Should Have | Fixed Price Per Card | Tasks to complete | Detail line | Store price in settings or model | Done | 100%
559 | Should Have | Fixed Price Per Card | Tasks to complete | Detail line | Display price on basket page | Done | 100%
560 | Should Have | Fixed Price Per Card | Tasks to complete | Detail line | Send correct price to Stripe | Done | 100%
561 | Should Have | Fixed Price Per Card | Tasks to complete | Detail line | Prevent user from editing price | Done | 100%
562 | Should Have | Fixed Price Per Card | Testing checklist | Section heading | Testing checklist: | Done | 100%
563 | Should Have | Fixed Price Per Card | Testing checklist | Blank line |  |  | 0%
564 | Should Have | Fixed Price Per Card | Testing checklist | Detail line | Price displays on basket page | Done | 100%
565 | Should Have | Fixed Price Per Card | Testing checklist | Detail line | Checkout uses correct amount | Done | 100%
566 | Should Have | Fixed Price Per Card | Testing checklist | Detail line | Price cannot be changed from frontend | Done | 100%
567 | Should Have | AI Usage Limit | Feature heading | Feature heading | AI Usage Limit | Done | 100%
568 | Should Have | AI Usage Limit | User request | Section heading | User request: | Done | 100%
569 | Should Have | AI Usage Limit | User request | Detail line | As a business/system, I want to limit AI generation so that API costs are controlled. | Done | 100%
570 | Should Have | AI Usage Limit | User request | Blank line |  |  | 0%
571 | Should Have | AI Usage Limit | How it can be done | Section heading | How it can be done: | Done | 100%
572 | Should Have | AI Usage Limit | How it can be done | Detail line | Each user has a limited number of AI background generations per 24 hours. | Done | 100%
573 | Should Have | AI Usage Limit | How it can be done | Blank line |  |  | 0%
574 | Should Have | AI Usage Limit | What needs to be included | Section heading | What needs to be included: | Done | 100%
575 | Should Have | AI Usage Limit | What needs to be included | Blank line |  |  | 0%
576 | Should Have | AI Usage Limit | What needs to be included | Detail line | Usage tracking | Done | 100%
577 | Should Have | AI Usage Limit | What needs to be included | Detail line | Daily limit | Done | 100%
578 | Should Have | AI Usage Limit | What needs to be included | Detail line | Error message when limit reached | Done | 100%
579 | Should Have | AI Usage Limit | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
580 | Should Have | AI Usage Limit | Tasks to complete | Blank line |  |  | 0%
581 | Should Have | AI Usage Limit | Tasks to complete | Detail line | Create AIUsage model or fields | Done | 100%
582 | Should Have | AI Usage Limit | Tasks to complete | Detail line | Track user, date, and generation count | Done | 100%
583 | Should Have | AI Usage Limit | Tasks to complete | Detail line | Check count before API call | Done | 100%
584 | Should Have | AI Usage Limit | Tasks to complete | Detail line | Increase count after successful generation | Done | 100%
585 | Should Have | AI Usage Limit | Tasks to complete | Detail line | Show warning when limit reached | Done | 100%
586 | Should Have | AI Usage Limit | Tasks to complete | Detail line | Display limit note in UI | Done | 100%
587 | Should Have | AI Usage Limit | Testing checklist | Section heading | Testing checklist: | Done | 100%
588 | Should Have | AI Usage Limit | Testing checklist | Blank line |  |  | 0%
589 | Should Have | AI Usage Limit | Testing checklist | Detail line | AI generation count increases | Done | 100%
590 | Should Have | AI Usage Limit | Testing checklist | Detail line | User cannot exceed limit | Done | 100%
591 | Should Have | AI Usage Limit | Testing checklist | Detail line | Limit resets after 24 hours/day | Done | 100%
592 | Should Have | AI Usage Limit | Testing checklist | Detail line | Clear message appears when limit reached | Done | 100%
593 | Should Have | Reset Form | Feature heading | Feature heading | Reset Form | Done | 100%
594 | Should Have | Reset Form | User request | Section heading | User request: | Done | 100%
595 | Should Have | Reset Form | User request | Detail line | As a user, I want to reset the card form so that I can start again easily. | Done | 100%
596 | Should Have | Reset Form | User request | Blank line |  |  | 0%
597 | Should Have | Reset Form | How it can be done | Section heading | How it can be done: | Done | 100%
598 | Should Have | Reset Form | How it can be done | Detail line | User clicks reset and the form clears selected values/message. | Done | 100%
599 | Should Have | Reset Form | How it can be done | Blank line |  |  | 0%
600 | Should Have | Reset Form | What needs to be included | Section heading | What needs to be included: | Done | 100%
601 | Should Have | Reset Form | What needs to be included | Blank line |  |  | 0%
602 | Should Have | Reset Form | What needs to be included | Detail line | Reset button | Done | 100%
603 | Should Have | Reset Form | What needs to be included | Detail line | Cleared form fields | Done | 100%
604 | Should Have | Reset Form | What needs to be included | Detail line | Cleared preview or default preview | Done | 100%
605 | Should Have | Reset Form | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
606 | Should Have | Reset Form | Tasks to complete | Blank line |  |  | 0%
607 | Should Have | Reset Form | Tasks to complete | Detail line | Add reset button | Done | 100%
608 | Should Have | Reset Form | Tasks to complete | Detail line | Use JavaScript or form reload | Done | 100%
609 | Should Have | Reset Form | Tasks to complete | Detail line | Clear message field | Done | 100%
610 | Should Have | Reset Form | Tasks to complete | Detail line | Reset counters | Done | 100%
611 | Should Have | Reset Form | Tasks to complete | Detail line | Clear preview placeholder | Done | 100%
612 | Should Have | Reset Form | Testing checklist | Section heading | Testing checklist: | Done | 100%
613 | Should Have | Reset Form | Testing checklist | Blank line |  |  | 0%
614 | Should Have | Reset Form | Testing checklist | Detail line | Reset clears form | Done | 100%
615 | Should Have | Reset Form | Testing checklist | Detail line | Counters return to 0 | Done | 100%
616 | Should Have | Reset Form | Testing checklist | Detail line | Preview returns to placeholder | Done | 100%
617 | Should Have | Empty State Messages | Feature heading | Feature heading | Empty State Messages | Done | 100%
618 | Should Have | Empty State Messages | User request | Section heading | User request: | Done | 100%
619 | Should Have | Empty State Messages | User request | Detail line | As a user, I want clear messages when I have no saved or purchased cards. | Done | 100%
620 | Should Have | Empty State Messages | User request | Blank line |  |  | 0%
621 | Should Have | Empty State Messages | How it can be done | Section heading | How it can be done: | Done | 100%
622 | Should Have | Empty State Messages | How it can be done | Detail line | Account and basket pages display helpful empty messages. | Done | 100%
623 | Should Have | Empty State Messages | How it can be done | Blank line |  |  | 0%
624 | Should Have | Empty State Messages | What needs to be included | Section heading | What needs to be included: | Done | 100%
625 | Should Have | Empty State Messages | What needs to be included | Blank line |  |  | 0%
626 | Should Have | Empty State Messages | What needs to be included | Detail line | Empty saved cards message | Done | 100%
627 | Should Have | Empty State Messages | What needs to be included | Detail line | Empty purchased cards message | Done | 100%
628 | Should Have | Empty State Messages | What needs to be included | Detail line | Empty basket message | Done | 100%
629 | Should Have | Empty State Messages | Tasks to complete | Section heading | Tasks to complete: | Done | 100%
630 | Should Have | Empty State Messages | Tasks to complete | Blank line |  |  | 0%
631 | Should Have | Empty State Messages | Tasks to complete | Detail line | Add conditional template logic | Done | 100%
632 | Should Have | Empty State Messages | Tasks to complete | Detail line | Write empty state text | Done | 100%
633 | Should Have | Empty State Messages | Tasks to complete | Detail line | Add link back to card creation page | Done | 100%
634 | Should Have | Empty State Messages | Testing checklist | Section heading | Testing checklist: | Done | 100%
635 | Should Have | Empty State Messages | Testing checklist | Blank line |  |  | 0%
636 | Should Have | Empty State Messages | Testing checklist | Detail line | Empty account sections display correctly | Done | 100%
637 | Should Have | Empty State Messages | Testing checklist | Detail line | Empty basket displays correctly | Done | 100%
638 | Should Have | Empty State Messages | Testing checklist | Detail line | Links work | Done | 100%
639 | Could Have |  | Priority heading | Priority heading | Could Have | Not Started | 0%
640 | Could Have | Multiple Card Formats | Feature heading | Feature heading | Multiple Card Formats | Not Started | 0%
641 | Could Have | Multiple Card Formats | User request | Section heading | User request: | Not Started | 0%
642 | Could Have | Multiple Card Formats | User request | Detail line | As a user, I want to choose a card format such as A4 or A5 so that I can download the size I prefer. | Not Started | 0%
643 | Could Have | Multiple Card Formats | User request | Blank line |  |  | 0%
644 | Could Have | Multiple Card Formats | How it can be done | Section heading | How it can be done: | Not Started | 0%
645 | Could Have | Multiple Card Formats | How it can be done | Detail line | User selects a format and the PDF is generated in that size. | Not Started | 0%
646 | Could Have | Multiple Card Formats | How it can be done | Blank line |  |  | 0%
647 | Could Have | Multiple Card Formats | What needs to be included | Section heading | What needs to be included: | Not Started | 0%
648 | Could Have | Multiple Card Formats | What needs to be included | Blank line |  |  | 0%
649 | Could Have | Multiple Card Formats | What needs to be included | Detail line | Format dropdown | Not Started | 0%
650 | Could Have | Multiple Card Formats | What needs to be included | Detail line | PDF size logic | Not Started | 0%
651 | Could Have | Multiple Card Formats | What needs to be included | Detail line | Format stored on card | Not Started | 0%
652 | Could Have | Multiple Card Formats | Tasks to complete | Section heading | Tasks to complete: | Not Started | 0%
653 | Could Have | Multiple Card Formats | Tasks to complete | Blank line |  |  | 0%
654 | Could Have | Multiple Card Formats | Tasks to complete | Detail line | Add format choices to Card model | Not Started | 0%
655 | Could Have | Multiple Card Formats | Tasks to complete | Detail line | Add format dropdown | Not Started | 0%
656 | Could Have | Multiple Card Formats | Tasks to complete | Detail line | Adjust PDF generation size | Not Started | 0%
657 | Could Have | Multiple Card Formats | Tasks to complete | Detail line | Display format in account/basket | Not Started | 0%
658 | Could Have | Multiple Card Formats | Testing checklist | Section heading | Testing checklist: | Not Started | 0%
659 | Could Have | Multiple Card Formats | Testing checklist | Blank line |  |  | 0%
660 | Could Have | Multiple Card Formats | Testing checklist | Detail line | User can choose format | Not Started | 0%
661 | Could Have | Multiple Card Formats | Testing checklist | Detail line | Format saves correctly | Not Started | 0%
662 | Could Have | Multiple Card Formats | Testing checklist | Detail line | PDF size changes correctly | Not Started | 0%
663 | Could Have | More Design Options | Feature heading | Feature heading | More Design Options | Not Started | 0%
664 | Could Have | More Design Options | User request | Section heading | User request: | Not Started | 0%
665 | Could Have | More Design Options | User request | Detail line | As a user, I want more themes, colours, and elements so that I have more variety. | Not Started | 0%
666 | Could Have | More Design Options | User request | Blank line |  |  | 0%
667 | Could Have | More Design Options | How it can be done | Section heading | How it can be done: | Not Started | 0%
668 | Could Have | More Design Options | How it can be done | Detail line | Admin adds more options through Django admin. | Not Started | 0%
669 | Could Have | More Design Options | How it can be done | Blank line |  |  | 0%
670 | Could Have | More Design Options | What needs to be included | Section heading | What needs to be included: | Not Started | 0%
671 | Could Have | More Design Options | What needs to be included | Blank line |  |  | 0%
672 | Could Have | More Design Options | What needs to be included | Detail line | Admin-managed options | Not Started | 0%
673 | Could Have | More Design Options | What needs to be included | Detail line | More database records | Not Started | 0%
674 | Could Have | More Design Options | What needs to be included | Detail line | Dropdowns update automatically | Not Started | 0%
675 | Could Have | More Design Options | Tasks to complete | Section heading | Tasks to complete: | Not Started | 0%
676 | Could Have | More Design Options | Tasks to complete | Blank line |  |  | 0%
677 | Could Have | More Design Options | Tasks to complete | Detail line | Add more sample themes | Not Started | 0%
678 | Could Have | More Design Options | Tasks to complete | Detail line | Add more colours | Not Started | 0%
679 | Could Have | More Design Options | Tasks to complete | Detail line | Add more elements | Not Started | 0%
680 | Could Have | More Design Options | Tasks to complete | Detail line | Test dropdown display | Not Started | 0%
681 | Could Have | More Design Options | Testing checklist | Section heading | Testing checklist: | Not Started | 0%
682 | Could Have | More Design Options | Testing checklist | Blank line |  |  | 0%
683 | Could Have | More Design Options | Testing checklist | Detail line | New options appear in form | Not Started | 0%
684 | Could Have | More Design Options | Testing checklist | Detail line | New options work with AI prompt | Not Started | 0%
685 | Could Have | More Design Options | Testing checklist | Detail line | New options save correctly | Not Started | 0%
686 | Won’t Have This Time |  | Priority heading | Priority heading | Won’t Have This Time | Not Started | 0%
687 | Won’t Have This Time | Drag-and-Drop Card Editor | Feature heading | Feature heading | Drag-and-Drop Card Editor | Not Started | 0%
688 | Won’t Have This Time | Drag-and-Drop Card Editor | User request | Section heading | User request: | Not Started | 0%
689 | Won’t Have This Time | Drag-and-Drop Card Editor | User request | Detail line | As a user, I would like to move text and images around freely on the card. | Not Started | 0%
690 | Won’t Have This Time | Drag-and-Drop Card Editor | User request | Blank line |  |  | 0%
691 | Won’t Have This Time | Drag-and-Drop Card Editor | How it could be done | Section heading | How it could be done: | Not Started | 0%
692 | Won’t Have This Time | Drag-and-Drop Card Editor | How it could be done | Detail line | A drag-and-drop editor could allow users to customise the layout manually. | Not Started | 0%
693 | Won’t Have This Time | Drag-and-Drop Card Editor | How it could be done | Blank line |  |  | 0%
694 | Won’t Have This Time | Drag-and-Drop Card Editor | What would be needed | Section heading | What would be needed: | Not Started | 0%
695 | Won’t Have This Time | Drag-and-Drop Card Editor | What would be needed | Blank line |  |  | 0%
696 | Won’t Have This Time | Drag-and-Drop Card Editor | What would be needed | Detail line | JavaScript drag-and-drop editor | Not Started | 0%
697 | Won’t Have This Time | Drag-and-Drop Card Editor | What would be needed | Detail line | Saved element positions | Not Started | 0%
698 | Won’t Have This Time | Drag-and-Drop Card Editor | What would be needed | Detail line | More complex PDF rendering | Not Started | 0%
699 | Won’t Have This Time | Drag-and-Drop Card Editor | What would be needed | Detail line | Advanced UI testing | Not Started | 0%
700 | Won’t Have This Time | Drag-and-Drop Card Editor | Reason not included | Section heading | Reason not included: | Not Started | 0%
701 | Won’t Have This Time | Drag-and-Drop Card Editor | Reason not included | Detail line | This would make the project too large for the available timeframe. | Not Started | 0%
702 | Won’t Have This Time | Drag-and-Drop Card Editor | Reason not included | Blank line |  |  | 0%
703 | Won’t Have This Time | Multiple Card Types | Feature heading | Feature heading | Multiple Card Types | Not Started | 0%
704 | Won’t Have This Time | Multiple Card Types | User request | Section heading | User request: | Not Started | 0%
705 | Won’t Have This Time | Multiple Card Types | User request | Detail line | As a user, I would like to create birthday cards, wedding cards, and other greeting cards. | Not Started | 0%
706 | Won’t Have This Time | Multiple Card Types | User request | Blank line |  |  | 0%
707 | Won’t Have This Time | Multiple Card Types | How it could be done | Section heading | How it could be done: | Not Started | 0%
708 | Won’t Have This Time | Multiple Card Types | How it could be done | Detail line | The system could support multiple card categories. | Not Started | 0%
709 | Won’t Have This Time | Multiple Card Types | How it could be done | Blank line |  |  | 0%
710 | Won’t Have This Time | Multiple Card Types | What would be needed | Section heading | What would be needed: | Not Started | 0%
711 | Won’t Have This Time | Multiple Card Types | What would be needed | Blank line |  |  | 0%
712 | Won’t Have This Time | Multiple Card Types | What would be needed | Detail line | Card type model | Not Started | 0%
713 | Won’t Have This Time | Multiple Card Types | What would be needed | Detail line | Different prompts per card type | Not Started | 0%
714 | Won’t Have This Time | Multiple Card Types | What would be needed | Detail line | Different template layouts | Not Started | 0%
715 | Won’t Have This Time | Multiple Card Types | What would be needed | Detail line | More testing | Not Started | 0%
716 | Won’t Have This Time | Multiple Card Types | Reason not included | Section heading | Reason not included: | Not Started | 0%
717 | Won’t Have This Time | Multiple Card Types | Reason not included | Detail line | The MVP focuses only on thank-you cards to keep the scope realistic. | Not Started | 0%
718 | Won’t Have This Time | Multiple Card Types | Reason not included | Blank line |  |  | 0%
719 | Won’t Have This Time | Public Card Gallery | Feature heading | Feature heading | Public Card Gallery | Not Started | 0%
720 | Won’t Have This Time | Public Card Gallery | User request | Section heading | User request: | Not Started | 0%
721 | Won’t Have This Time | Public Card Gallery | User request | Detail line | As a user, I would like to share my cards publicly. | Not Started | 0%
722 | Won’t Have This Time | Public Card Gallery | User request | Blank line |  |  | 0%
723 | Won’t Have This Time | Public Card Gallery | How it could be done | Section heading | How it could be done: | Not Started | 0%
724 | Won’t Have This Time | Public Card Gallery | How it could be done | Detail line | Users could choose to publish cards to a public gallery. | Not Started | 0%
725 | Won’t Have This Time | Public Card Gallery | How it could be done | Blank line |  |  | 0%
726 | Won’t Have This Time | Public Card Gallery | What would be needed | Section heading | What would be needed: | Not Started | 0%
727 | Won’t Have This Time | Public Card Gallery | What would be needed | Blank line |  |  | 0%
728 | Won’t Have This Time | Public Card Gallery | What would be needed | Detail line | Public/private card settings | Not Started | 0%
729 | Won’t Have This Time | Public Card Gallery | What would be needed | Detail line | Gallery page | Not Started | 0%
730 | Won’t Have This Time | Public Card Gallery | What would be needed | Detail line | Moderation tools | Not Started | 0%
731 | Won’t Have This Time | Public Card Gallery | What would be needed | Detail line | Privacy controls | Not Started | 0%
732 | Won’t Have This Time | Public Card Gallery | Reason not included | Section heading | Reason not included: | Not Started | 0%
733 | Won’t Have This Time | Public Card Gallery | Reason not included | Detail line | Cards may contain personal messages, so privacy is prioritised. | Not Started | 0%
734 | Won’t Have This Time | Public Card Gallery | Reason not included | Blank line |  |  | 0%
735 | Won’t Have This Time | Real Production Payments | Feature heading | Feature heading | Real Production Payments | Not Started | 0%
736 | Won’t Have This Time | Real Production Payments | User request | Section heading | User request: | Not Started | 0%
737 | Won’t Have This Time | Real Production Payments | User request | Detail line | As a business owner, I would like to accept real customer payments. | Not Started | 0%
738 | Won’t Have This Time | Real Production Payments | User request | Blank line |  |  | 0%
739 | Won’t Have This Time | Real Production Payments | How it could be done | Section heading | How it could be done: | Not Started | 0%
740 | Won’t Have This Time | Real Production Payments | How it could be done | Detail line | Stripe could be switched from test mode to live mode. | Not Started | 0%
741 | Won’t Have This Time | Real Production Payments | How it could be done | Blank line |  |  | 0%
742 | Won’t Have This Time | Real Production Payments | What would be needed | Section heading | What would be needed: | Not Started | 0%
743 | Won’t Have This Time | Real Production Payments | What would be needed | Blank line |  |  | 0%
744 | Won’t Have This Time | Real Production Payments | What would be needed | Detail line | Live Stripe keys | Not Started | 0%
745 | Won’t Have This Time | Real Production Payments | What would be needed | Detail line | Legal/business setup | Not Started | 0%
746 | Won’t Have This Time | Real Production Payments | What would be needed | Detail line | Refund handling | Not Started | 0%
747 | Won’t Have This Time | Real Production Payments | What would be needed | Detail line | Production payment security checks | Not Started | 0%
748 | Won’t Have This Time | Real Production Payments | Reason not included | Section heading | Reason not included: | Not Started | 0%
749 | Won’t Have This Time | Real Production Payments | Reason not included | Detail line | The project uses Stripe test mode for demonstration and assessment purposes. | Not Started | 0%

## Completion Summary
Completion Summary by Main Issue
Priority Group | Main Issue / Feature | Total Detail Lines | Done | In Progress | Not Started / Blank | Completion % | Deadline
Must Have (MVP) | Home Page / Card Creation Page | 24 | 24 | 0 | 0 | 100%
Must Have (MVP) | User Registration | 22 | 22 | 0 | 0 | 100%
Must Have (MVP) | User Login & Logout | 20 | 20 | 0 | 0 | 100%
Must Have (MVP) | Password Reset | 16 | 16 | 0 | 0 | 100% | 2026-05-17
Must Have (MVP) | Select Card Options | 24 | 24 | 0 | 0 | 100%
Must Have (MVP) | Generate AI Background | 25 | 25 | 0 | 0 | 100%
Must Have (MVP) | Add Recipient Name | 17 | 17 | 0 | 0 | 100%
Must Have (MVP) | Add / Generate / Improve Message | 25 | 25 | 0 | 0 | 100% | 2026-05-24
Must Have (MVP) | No Message Option | 17 | 17 | 0 | 0 | 100%
Must Have (MVP) | Preview Card Before Payment | 19 | 19 | 0 | 0 | 100%
Must Have (MVP) | Save Card | 19 | 19 | 0 | 0 | 100%
Must Have (MVP) | Edit Saved Card | 20 | 20 | 0 | 0 | 100%
Must Have (MVP) | Delete Saved Card | 18 | 18 | 0 | 0 | 100%
Must Have (MVP) | Account Page | 20 | 20 | 0 | 0 | 100% | 2026-05-31
Must Have (MVP) | Basket Page | 23 | 23 | 0 | 0 | 100%
Must Have (MVP) | Payment / Checkout | 22 | 22 | 0 | 0 | 100%
Must Have (MVP) | Download PDF | 21 | 21 | 0 | 0 | 100%
Should Have | Fixed Price Per Card | 14 | 14 | 0 | 0 | 100%
Should Have | AI Usage Limit | 15 | 15 | 0 | 0 | 100%
Should Have | Reset Form | 13 | 13 | 0 | 0 | 100%
Should Have | Empty State Messages | 11 | 11 | 0 | 0 | 100% | 2026-06-07
Could Have | Multiple Card Formats | 12 | 0 | 0 | 12 | 0%
Could Have | More Design Options | 12 | 0 | 0 | 12 | 0%
Won’t Have This Time | Drag-and-Drop Card Editor | 7 | 0 | 0 | 7 | 0%
Won’t Have This Time | Multiple Card Types | 7 | 0 | 0 | 7 | 0%
Won’t Have This Time | Public Card Gallery | 7 | 0 | 0 | 7 | 0%
Won’t Have This Time | Real Production Payments | 7 | 0 | 0 | 7 | 0%
Overall Summary by Priority
Priority Group | Total Detail Lines | Done | In Progress | Completion %
Must Have (MVP) | 352 | 352 | 0 | 100%
Should Have | 53 | 53 | 0 | 100%
Could Have | 24 | 0 | 0 | 0%
Won’t Have This Time | 28 | 0 | 0 | 0%